## Sheet1
CapT Openhouse
Timeline | Task | Club Executive
6-8 weeks | Assign a committee & set budget
6-8 weeks | Set date with VP Education, VP Membership & VP PR
Communicate date to Club Members
Plan Public Relations campaign - The key to your success!!
Invite local politician if appropriate
Arrange for Guest Speaker - creates buzz and excitement!
Approach experienced members for key roles - puts on a good show
Invite Area, Division & District dignitaries & put on agenda
Invite Past Members to attend - they might re-join
Invite Founding Members, Club Sponsors/Mentors/Coaches
Ask Club Memebers to "Bring a Friend"
Pick an appropriate theme for the meeting (new beginnings, achievement, etc
Pick a Word of the Day that matches the occasion
Prepare a suitable Table Topics session
Select speakers who will represent the club effectively
Prepare Open House packages/New Memebr kits
Consider an incentive to join the day of the Open House (with club approval)
Timeline | Task
2 weeks before | Name tags purchased/prepared | Committee
Finalize Agenda
Decorations? Make it fun & festive!
Cake? - (Yellow & Blue theme)
Food? (Consider dietary restrictions when planning)
Supplies for food (plates, forks, napkins, cups)
Finalize incentive if using (gift card, draw, slight discount to fees, etc)
Print ample supply of "Agendas"
1 hour before | Set up room theater style & test AV equipment
Committee & Club Executives arrive early & set the welcoming tone
Guest Greeters arrive early & set up welcome area
Guest Book, Open House Packets available
During Meeting | Welcome Guests
Allow guests to participate in Table Topics
Explain all parts of meetin and the purpose of it
Thank the guest and dignitaries
Thank the organizing committee
Invite everyone to sign up or come back (Call to action is needed)